## 1 - Structure, spaces and hardware
Naming of spaces		/home/dominique/Arduino/Documentation/Robotics general notes/vehicule_spaces_v1.odt
Space allocation
1.0	Vehicule structure
1.1	Space plan: naming of plates, bulkhead and decks	see file above
1.2	aB Decks: adding a hole to secure mounting
1.3	aB Decks: prepare mounting for H-bridge enclosure
1.4	eF Decks: adding two holes to secure standoffs

## 2 - Motor control
DEVELOPPEMENT

2.0	Motors control and H-Bridge – testings and developement		Results	STATUS
	2.1 Wiring L298N to Arduino Due for Motor control – Direction and speed only		Fig. 2.1 wiring diagram
	2.2 Sketch moteurs_v2.ino: determine wiring for motor direction control at full speed		success in determining motor control
	2.3 L298N to Arduino Due for Motor control using PID
		2.3.1 empty section
		2.3.2 Wiring motor Hall sensors to Arduino Due via level shifter	wiring table
		2.3.4 Sketch motor_PID_v1.ino using interrup and button to change motor direction	see notes, procedure abandonned
	2.4 testing motor control using a joystick: sketch motors_joystick_v1.ino		Using joystick on breakout board. Success, but this device will not be used in this context
	2.5 correcting motor rotation direction		Fig. 2.1 wiring diagram corrected
	2.6 motor control functions: sketch motors_joystick_v1.ino		The functions for controling the motors are corrected according to finding in section 2.5
	2.7 Measuring the speed motors M1, M2 and M3: sketch motors_measures_v1.ino
		2.7.1 Objectives	Explanation of procedure and Fig 2 diagram of IR sensor placement relative to motor
		2.7.2 Preliminary results for motors M1 and M2	Developpement of procedure only - results not taken into account
	2.8 Measuring the speed motors M1, M2 and M3: sketch motors_measures_v2.ino
		2.8.1 changes from sketch v1 to v2	Mainly use of DueTimer Library and provision to mesure drive wheel speed directly uning IR sensor
		2.8.2 Preliminary results for motor M1 and M2	Developpement of procedure only - results not taken into account
		2.8.3 Measuring motor M1, M2 and M3: sketch motors_measures_v3.ino
		2.8.3.1 changes from version 2
		2.8.3.2 Measuring motors	Table of procedure and files 2.8.3.2.1
		2.8.3.3 Data analysis	in progress :: data inserted in speadsheets done
		2.8.3.4 Conclusion

	2.9 Find the balance between the two motors: is this necessary???
		Right motor runs faster than left at pwm 255. Using the date from Hall sensors, find the correct value to get approximate same speed

	2.10 Teleoperating the motors with a PS2 remote game controler

	2.11 operating the motors using functions for directionnal control
		PID for moving in a streight line
		PID for turning on the spot
		Turning: stop and turn implementation
		Turning: turn as we go implementation

IMPLEMENTATION – INTEGRATION

2.1	H-Bridge main power and logic power wiring
	2.1.1	Mounting H-bridge in watertight enclosure
	2.1.2	Motor power lines to main power source 10.4 VDC
	2.1.3	H-bridge circuit power line to 5 VDC power rail
	2.1.4	H-bridge logic control signal lines to Arduino via 5V-3.3 VDC level shifter

2.2	Motor testing and calibration
	2.2.1	Motors M1, M2 and M3: speed tests using internal Hall sensors and temporary external optical IR sensors
	2.2.2	Motors: selecting best pair between M1, M2 and M3
	2.2.3	Motor power lines to H-bridge
	2.2.4	blank
	2.2.5	Motor Hall encoders power to 5VDC power rail
	2.2.6	Motor Hall encoders logic signal to Arduino via 5V-3.3 VDC level shifter
	2.2.7	Connect temperature sensors to Arduino via 5V-3.3 VDC level shifter

## 3 - Level shifting 3.3V-5V logic bus
3. Level shifting 3.3V-5V logic bus

## 4 - Power supply
Battery compartment assembly
Power control panel: switches and DELs
Venom Low voltage indicator

Mounting batteries - power management - 5 VDC power bus - 3.3 VDC power bus.

## 5 - Software
Motor tests and calibrations
	Motors M1, M2 and M3: speed tests using internal Hall sensors and remporary external optical IR sensors
	Motors: selecting best pair between M1, M2 and M3
	Motors mounted in close proximity: determine if Hall sensors affect each other.
	Motor calibration: formula for calculating drive wheel speed from Hall sensors readings
	Motors: measuring direction from Hall sensors readings

Motor control
	Controling motors with a joystick (TELEOP mode).
	Controling motors by software (not TELEOP mode) while regulating motors speed with PID, no turns.
	Controling motors by software (not TELEOP mode) while regulating motors speed with PID, including turns.

Study requirement for a (logic shifting 5 VDC to) 3.3 VDC logic bus.

## 7 - Sensors
7.0	Sensors
	'7.1 Motors TMP36 temperature sensors
		'7.1.1 Left Motor TMP36 temperature sensor:
			test unwired sensor
			wire sensor
			test wired sensor
			mount sensor to Left motor
			test mounted sensor

		'7.1.2 Right Motor TMP36 temperature sensor:
			test unwired sensor
			wire sensor
			test wired sensor
			mount sensor to Right motor
			test mounted sensor